## Cover
Software Functional Test Summary Report
<22914> - <ROW>
Prepared by | Wang, Yuxiang
Approved by | Wan, Tao
YanFeng Visteon Electronics Technology (Shanghai) Co., Ltd

## Histroy
Revision History
Version | Section/Page | Description | Date | Revised By
V1.0.0 | Summary | Changed field against. | 2016-10-27 | Yuxiang Wang

## Summary
SW_ROW_7482_Functional_Test_Summary_Report
Total: All software defects found in this project which filed against status is "Software";
Open: All open defects which filed against status is "Development" and RTC state not in 'Closed';
New: The software defects found in currunt version;
Closed: All software defects closed in current version;
Reopened: The software defects reopened in current version;
Invalid: The invaild defects found by Development team.
NO. | Milestone |  | Defects
|  |  | Total | Open | New | Closed | Reopened | Invalid
1 | C Sample(7420_Y509) |  | 32 | 32 | 26 | 67 | 0 | 0
2 | SOP(7431_Y510) |  | 29 | 29 | 8 | 50 | 0 | 0
3 | SOP(7440_Y511) |  | 12 | 12 | 8 | 10 | 0 | 0
4 | SOP(7441_Y511) |  | 7 | 7 | 7 | 22 | 0 | 0
5 | SOP(7450_Y512) |  | 9 | 9 | 4 | 31 | 1 | 0
6 | SOP(7451_Y512) |  | 17 | 17 | 15 | 9 | 1 | 0
7 | SOP(7460_5513) |  | 12 | 12 | 2 | 18 | 0 | 0
8 | SOP(7461_5513) |  | 13 | 13 | 10 | 15 | 0 | 0
9 | SOP(7470_5514) |  | 14 | 14 | 10 | 6 | 1 | 0
10 | SOP(7481_5515) |  | 4 | 4 | 2 | 31 | 0 | 0
11 | SOP(7482_5515) |  | 13 | 13 | 11 | 5 | 1 | 0
Defects Metrics
NO. | Feature List | Total Defects | Critical | High | Medium | Low
1 | HMI | 5 | 0 | 1 | 3 | 1
2 | Audio | 1 | 0 | 0 | 1 | 0
3 | Diag | 0 | 0 | 0 | 0 | 0
4 | Network | 0 | 0 | 0 | 0 | 0
5 | Tuner | 0 | 0 | 0 | 0 | 0
6 | BT | 2 | 0 | 0 | 2 | 0
7 | Infrastructure | 0 | 0 | 0 | 0 | 0
8 | Media | 0 | 0 | 0 | 0 | 0
9 | Power | 0 | 0 | 0 | 0 | 0
10 | EOL | 0 | 0 | 0 | 0 | 0
11 | Software | 2 | 0 | 0 | 2 | 0
12 | Integration | 0 | 0 | 0 | 0 | 0
13 | BSP | 0 | 0 | 0 | 0 | 0
14 | Display | 3 | 0 | 0 | 3 | 0
15 | VIP_Service | 0 | 0 | 0 | 0 | 0
16 | Connectivity | 0 | 0 | 0 | 0 | 0
17 | BAP | 0 | 0 | 0 | 0 | 0
18 | Power Agent | 0 | 0 | 0 | 0 | 0
19 | EXLAP | 0 | 0 | 0 | 0 | 0
20 | Carlife | 0 | 0 | 0 | 0 | 0
21 | CarPlay | 0 | 0 | 0 | 0 | 0
22 | Display_YF | 0 | 0 | 0 | 0 | 0
23 | AAP | 0 | 0 | 0 | 0 | 0
Total |  | 13 | 0 | 1 | 11 | 1

## 7.4.8.2
ROW_7482 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | 5515 |  |  |  | Bench | 2
S/W Version |  | 7482 |  |  |  | SD | 6
H/W Version |  | 555 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2017-04-20
End Date |  | 2017-04-20
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Zhang Yunge | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | N |  |  |  | No change.
18 | Power | Y | Rex | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | N |  |  |  | No change.
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 5 |  | 1 | 3 | 1
2 | Audio | 1 |  | 0 | 1 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 1 |  | 0 | 1 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 0 |  | 0 | 0 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 2 |  | 0 | 2 | 0
12 | Integration | 0 |  | 0 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 2 |  | 0 | 2 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 0 |  | 0 |  | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 0 |  | 0 |  | 0
Total |  | 11 | 0 | 1 | 9 | 1
Percentage(%) |  |  | 0% | 9.091% | 81.82% | 9.091%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 11 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 5
3 | Closed in current version |  | 5
4 | Reopened in current version |  | 1
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 16.67%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7482(ROW_5515)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.8.1
ROW_7481 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | 5515 |  |  |  | Bench | 2
S/W Version |  | 7481 |  |  |  | SD | 6
H/W Version |  | 555 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2017-04-13
End Date |  | 2017-04-13
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Zhang Yunge | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | N |  |  |  | No change.
18 | Power | Y | Rex | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | N |  |  |  | No change.
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 7 |  | 5 | 2 | 0
2 | Audio | 0 |  | 0 | 0 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 0 |  | 0 | 0 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 1 |  | 0 | 1 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 0 |  | 0 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 0 |  | 0 | 0 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 1 |  | 1 | 0 | 0
17 | BAP | 1 |  | 1 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 0 |  | 0 |  | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 0 |  | 0 |  | 0
Total |  | 10 | 0 | 7 | 3 | 0
Percentage(%) |  |  | 0% | 70% | 30% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 10 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 6
3 | Closed in current version |  | 6
4 | Reopened in current version |  | 1
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 14.29%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7481(ROW_5515)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.7.0
ROW_7470 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | 5514 |  |  |  | Bench | 2
S/W Version |  | 7470 |  |  |  | SD | 6
H/W Version |  | 555 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2017-03-06
End Date |  | 2017-03-06
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Zhang Yunge | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | N |  |  |  | No change.
18 | Power | Y | Rex | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | N |  |  |  | No change.
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 7 |  | 5 | 2 | 0
2 | Audio | 0 |  | 0 | 0 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 0 |  | 0 | 0 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 1 |  | 0 | 1 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 0 |  | 0 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 0 |  | 0 | 0 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 1 |  | 1 | 0 | 0
17 | BAP | 1 |  | 1 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 0 |  | 0 |  | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 0 |  | 0 |  | 0
Total |  | 10 | 0 | 7 | 3 | 0
Percentage(%) |  |  | 0% | 70% | 30% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 10 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 6
3 | Closed in current version |  | 6
4 | Reopened in current version |  | 1
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 14.29%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7470(ROW_5514)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.6.1
ROW_7461 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | 5513 |  |  |  | Bench | 2
S/W Version |  | 7461 |  |  |  | SD | 6
H/W Version |  | 554 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2017-02-21
End Date |  | 2017-02-21
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Zhang Yunge | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | N |  |  |  | No change.
18 | Power | Y | Rex | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | N |  |  |  | No change.
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 4 |  | 0 | 4 | 0
2 | Audio | 2 |  | 1 | 1 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 0 |  | 0 | 0 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 2 |  | 0 | 2 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 2 |  | 0 | 2 | 0
12 | Integration | 0 |  | 0 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 0 |  | 0 | 0 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 0 |  | 0 |  | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 0 |  | 0 |  | 0
Total |  | 10 | 0 | 1 | 9 | 0
Percentage(%) |  |  | 0% | 10% | 90% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 12 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 15
3 | Closed in current version |  | 15
4 | Reopened in current version |  | 0
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 0%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7461(ROW_5513)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.6.0
ROW_7460 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | 5513 |  |  |  | Bench | 2
S/W Version |  | 7460 |  |  |  | SD | 6
H/W Version |  | 554 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2017-02-12
End Date |  | 2017-02-12
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Zhang Yunge | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | N |  |  |  | No change.
18 | Power | Y | Rex | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | N |  |  |  | No change.
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 0 |  | 0 | 0 | 0
2 | Audio | 0 |  | 0 | 0 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 0 |  | 0 | 0 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 0 |  | 0 | 0 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 2 |  | 2 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 0 |  | 0 | 0 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 0 |  | 0 |  | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 0 |  | 0 |  | 0
Total |  | 2 | 0 | 2 | 0 | 0
Percentage(%) |  |  | 0% | 100% | 0% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 2 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 18
3 | Closed in current version |  | 18
4 | Reopened in current version |  | 0
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 0%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7460(ROW_5513)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.5.1
ROW_7451 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | Y512 |  |  |  | Bench | 2
S/W Version |  | 7451 |  |  |  | SD | 6
H/W Version |  | 554 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2017-01-20
End Date |  | 2017-01-20
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Zhang Yunge | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | N |  |  |  | No change.
18 | Power | Y | Rex | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | N |  |  |  | No change.
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 5 |  | 2 | 3 | 0
2 | Audio | 2 |  | 0 | 2 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 3 |  | 3 | 0 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 0 |  | 0 | 0 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 1 |  | 0 | 0 | 1
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 1 |  | 1 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 1 |  | 0 | 0 | 1
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 2 |  | 2 |  | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 0 |  | 0 |  | 0
Total |  | 15 | 0 | 8 | 5 | 2
Percentage(%) |  |  | 0% | 53.33% | 33.33% | 13.33%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 15 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 9
3 | Closed in current version |  | 9
4 | Reopened in current version |  | 1
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 10%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7451(ROW_Y512)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.5.0
ROW_7450 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | Y512 |  |  |  | Bench | 2
S/W Version |  | 7450 |  |  |  | SD | 6
H/W Version |  | 554 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2017-01-16
End Date |  | 2017-01-16
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Zhang Yunge | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | N |  |  |  | No change.
18 | Power | Y | Rex | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | N |  |  |  | No change.
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 1 |  | 1 | 0 | 0
2 | Audio | 0 |  | 0 | 0 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 1 |  | 0 | 1 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 2 |  | 1 | 1 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 0 |  | 0 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 0 |  | 0 | 0 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 0 |  | 0 |  | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 0 |  | 0 |  | 0
Total |  | 4 | 0 | 2 | 2 | 0
Percentage(%) |  |  | 0% | 50% | 50% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 4 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 31
3 | Closed in current version |  | 31
4 | Reopened in current version |  | 1
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 3.125%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7450(ROW_Y512)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.4.1
ROW_7441 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | Y511 |  |  |  | Bench | 2
S/W Version |  | 7441 |  |  |  | SD | 6
H/W Version |  | 554 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2016-12-14
End Date |  | 2016-12-14
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Liu Jianbo | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | Y | Liu Jianbo | 183 | 0
18 | Power | Y | Xu Chuanming | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | Y | Rex | 70 | 0
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 3 |  | 1 | 2 | 0
2 | Audio | 0 |  | 0 | 0 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 2 |  | 0 | 2 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 0 |  | 0 | 0 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 0 |  | 0 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 0 |  | 0 | 0 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 1 |  | 0 | 1 | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 1 |  | 0 | 1 | 0
Total |  | 7 | 0 | 1 | 6 | 0
Percentage(%) |  |  | 0% | 14.29% | 85.71% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 7 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 22
3 | Closed in current version |  | 22
4 | Reopened in current version |  | 0
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 0%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7441(ROW_Y511)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.4.0
ROW_7440 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | Y511 |  |  |  | Bench | 2
S/W Version |  | 7440 |  |  |  | SD | 6
H/W Version |  | MQB:Y53;PQ:552 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2016-12-14
End Date |  | 2016-12-14
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Liu Jianbo | 31 | 0
8 | Climate | Y | Wang Yuxiang | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | Y | Liu Jianbo | 183 | 0
18 | Power | Y | Xu Chuanming | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Rex | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | Y | Rex | 70 | 0
24 | Remote control | N |  |  |  | No change.
25 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 2 |  | 1 | 1 | 0
2 | Audio | 1 |  | 0 | 1 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 1 |  | 1 | 0 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 0 |  | 0 | 0 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 0 |  | 0 | 0 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 0 |  | 0 | 0 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 1 |  | 1 | 0 | 0
21 | CarPlay | 0 |  | 0 | 0 | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 3 |  | 0 | 3 | 0
Total |  | 8 | 0 | 3 | 5 | 0
Percentage(%) |  |  | 0% | 37.5% | 62.5% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 8 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 10
3 | Closed in current version |  | 10
4 | Reopened in current version |  | 0
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 0%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7440(ROW_Y511)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.3.1
ROW_7431 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu |  |  |  | CANoe | 2
Customer Version |  | Y510 |  |  |  | Bench | 2
S/W Version |  | 7431 |  |  |  | SD | 6
H/W Version |  | MQB:Y53;PQ:552 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2016-11-18
End Date |  | 2016-11-18
NO. of Days |  | 1
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Rex | 95 | 0
2 | Beep | N |  |  |  | No change.
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 142 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife | N |  |  |  | No change.
7 | CarPlay | Y | Liu Jianbo | 31 | 0
8 | Climate | Y | Binu | 76 | 0
9 | Color | N |  |  |  | No change.
10 | Diag | N |  |  |  | No change.
11 | EOL | N |  |  |  | No change.
12 | ETM | N |  |  |  | No change.
13 | HMI | N |  |  |  | No change.
14 | iPod | N |  |  |  | No change.
15 | SD | N |  |  |  | No change.
16 | USB | N |  |  |  | No change.
17 | MirrorLink | Y | Liu Jianbo | 183 | 0
18 | Power | Y | Xu Chuanming | 220 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 71 | 0
20 | Safe | Y | Xu Chuanming | 41 | 0
21 | Setup | N |  |  |  | No change.
22 | Speller | N |  |  |  | No change.
23 | Tuner | Y | Binu | 70 | 0
24 | Remote control | Y | Rex | 28 | 0
25 | Safe code | Y | Xu Chuanming | 44 | 0
26 | Upgrading | N |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | HMI | 12 |  | 0 | 12 | 0
2 | Audio | 1 |  | 1 | 0 | 0
3 | Diag | 0 |  | 0 | 0 | 0
4 | Network | 0 |  | 0 | 0 | 0
5 | Tuner | 0 |  | 0 | 0 | 0
6 | BT | 2 |  | 0 | 2 | 0
7 | Infrastructure | 0 |  | 0 | 0 | 0
8 | Media | 0 |  | 0 | 0 | 0
9 | Power | 0 |  | 0 | 0 | 0
10 | EOL | 0 |  | 0 | 0 | 0
11 | Software | 0 |  | 0 | 0 | 0
12 | Integration | 1 |  | 0 | 1 | 0
13 | BSP | 0 |  | 0 | 0 | 0
14 | Display | 1 |  | 0 | 1 | 0
15 | VIP_Service | 0 |  | 0 | 0 | 0
16 | Connectivity | 0 |  | 0 | 0 | 0
17 | BAP | 0 |  | 0 | 0 | 0
18 | Power Agent | 0 |  | 0 | 0 | 0
19 | EXLAP | 0 |  | 0 | 0 | 0
20 | Carlife | 0 |  | 0 | 0 | 0
21 | CarPlay | 4 |  | 0 | 4 | 0
22 | Display_YF | 0 |  | 0 | 0 | 0
23 | AAP | 1 |  | 0 | 1 | 0
Total |  | 22 | 0 | 1 | 21 | 0
Percentage(%) |  |  | 0% | 4.545% | 95.45% | 0%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 22 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 91
3 | Closed in current version |  | 50
4 | Reopened in current version |  | 0
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 0%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7431(ROW_Y510)
Note on H25: Author: If Implemented is no, need fill the comments

## 7.4.2.0
ROW_7420 Software Functional Test Report
Test Information | [5 empty] | Test Equipment
EnterProj# |  | 22914 |  |  |  | Name | Quantity
Tester |  | Wang Yuxiang;Liu Jianbo;Zhang Yunge;Xu Chuanming;Rex;Binu;Saranya |  |  |  | CANoe | 2
Customer Version |  | Y509 |  |  |  | Bench | 2
S/W Version |  | 7420 |  |  |  | SD | 6
H/W Version |  | Y52 |  |  |  | USB | 6
Test Cycle |  | 1 |  |  |  | iPhone | 2
Start Date |  | 2016-10-24
End Date |  | 2016-10-25
NO. of Days |  | 2
Reference File |  | SRS
Reference Procedure |  | FT V1.4
Test result |  | Pass
Analysis
2.Features Implemented Status
NO. | Feature List | Implemented | Tester | Pass | Fail | Comment
1 | Android Auto | Y | Saranya | 87 | 0
2 | Beep |  |  |  |  | No Change
3 | BT_Audio | Y | Zhang Yunge | 66 | 0
4 | BT_Phone | Y | Zhang Yunge | 125 | 0
5 | Car | Y | Wang Yuxiang | 321 | 0
6 | Carlife |  |  |  |  | No Change
7 | CarPlay | Y | Liu Jianbo | 30 | 0
8 | Climate | Y | Binu | 76 | 0
9 | Color |  |  |  |  | No Change
10 | Diag |  |  |  |  | No Change
11 | EOL |  |  |  |  | No Change
12 | ETM |  |  |  |  | No Change
13 | HMI |  |  |  |  | No Change
14 | iPod | Y | Binu | 63 | 0
15 | SD |  |  |  |  | No Change
16 | USB |  |  |  |  | No Change
17 | MirrorLink | Y | Liu Jianbo | 183 | 0
18 | Power | Y | Xu Chuanming | 33 | 0
19 | RVC&OPS | Y | Wang Yuxiang | 70 | 0
20 | Safe | Y | Xu Chuanming | 41 | 0
21 | Setup |  |  |  |  | No Change
22 | Speller |  |  |  |  | No Change
23 | Tuner | Y | Saranya | 79 | 0
24 | Upgrading |  |  |  |  | Only test via USB updating but not follow the test case fully.
3.New Defects Metrics
NO. | Feature List | New Defects | Critical | High | Medium | Low
1 | Speedometer | 0 |  | 0 | 0 | 0
2 | Tachometer | 1 |  | 1 | 0 | 0
3 | Temperature | 1 |  | 0 | 0 | 1
4 | Fuel | 1 |  | 1 | 0 | 0
5 | Telltale | 5 |  | 2 | 3 | 0
6 | ODO/Trip | 0 |  | 0 | 0 | 0
7 | Gear | 0 |  | 0 | 0 | 0
8 | Gear | 0 |  | 0 | 0 | 0
9 | Gear | 0 |  | 0 | 0 | 0
10 | Gear | 0 |  | 0 | 0 | 0
11 | Trip Computer | 12 |  | 9 | 3 | 0
12 | Warning | 1 |  | 1 | 0 | 0
13 | Illumination | 1 |  | 0 | 1 | 0
14 | Chime | 5 | 5 | 0 | 0 | 0
15 | ETM | 0 |  | 0 | 0 | 0
16 | Boot loader | 6 | 6 | 0 | 0 | 0
17 | PPM | 0 |  | 0 | 0 | 0
18 | Diagnostic | 1 |  | 1 | 0 | 0
19 | Power Management | 2 |  | 1 | 1 | 0
20 | FBL | 1 |  | 0 | 1 | 0
Total |  | 37 | 11 | 16 | 9 | 1
Percentage(%) |  |  | 29.73% | 43.24% | 24.32% | 2.703%
4.Defects Status
NO. | State |  | Defects Quantity
1 | New defects in current version |  | 26 |  |  | [Total fixed defects]: The defects found by validation team are "Resolved" status in RTC; [Closed in current version]: The defects status is changed to "Closed" from "Resolved" in current version. [Reopened in current version]: The defects status from "Resolved" to "Reopened" in current version.
2 | Total fixed defects |  | 107
3 | Closed in current version |  | 67
4 | Reopened in current version |  | 0
5 | Without verify condition in current version |  | 0
6 | Reopened defects rate |  | 0%
5. Test Report and result path
\\136.17.77.226\Softwares\ReleaseReport_6.5inch\ROW\7420(ROW_Y509)
Note on H25: Author: If Implemented is no, need fill the comments